## Sheet1
Implimentation Progress
| WEEK |  |  |  |  | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32
TASK | ASSIGNED TO | PROGRESS | START DATE | END DATE | No. Of Days | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
1 - Initiation | time axis 2026-04-01 to 2026-08-04
Tenant Creation/Kick Off | SI
Design workshop | SI/UPPCL
Project Tracker creation | SI
Project Plan Sign-off | UPPCL
2 - Design & Pre-requisites
Pre-requisites Sharing | SI |  | 2026-06-04 | 2026-06-04 | bar: 2026-06-04
HLD doc creation and review | SI |  | 2026-07-04 | 2026-10-04 | bar: 2026-07-04 to 2026-08-04
HLD doc initial draft review | UPPCL |  | 13/4/2026 | 13/4/2026
HLD doc sign off | UPPCL |  | 14/4/2026 | 14/4/2026
Pre-requisites confirmation | UPPCL |  | 15/4/2026 | 15/4/2026
3.User provisioning & Tenant SSO
SCIM Integration/ Directory importer deployment | SI/UPPCL |  | 16/4/2026 | 16/4/2026
Configure SCIM API or AD sync to sync users/groups to tenant | SI/UPPCL |  | 17/4/2026 | 17/4/2026
Validate users/groups are pushed successfully to tenant | SI/UPPCL |  | 20/4/2026 | 21/4/2026
4.NG-SWG (with DEM,UEBA,CFW & Threat Protection)
Netskope Best practice policy configuration | SI |  | 22/4/2026 | 24/4/2026
Create threat protection profile (File Hash List: Whitelist, Blacklist) and inline policy | SI |  | 27/4/2026 | 30/4/2026
Configuration of NGSWG (SWG,CASB,UEBA,DEIP policiesas per requirement shared by UPPCL | SI |  | 2026-01-05 | 2026-05-05
Fine-tuning of access policies as per UAT | SI |  | 2026-06-05 | 2026-08-05
Phase-/department-wise rollout | SI/UPPCL |  | 2026-11-05 | 15/5/26
Sign-off for NGSWG Implementation | UPPCL |  | 18/5/26 | 20/5/26
Install and configure Log Server for SIEM integration Validate events are seen in SIEM solution | SI/UPPCL |  | 21/5/26 | 26/5/26
Information Gathering for CFW (application name, destination IP/FQDN, protocol, destination ports from existing solution) if applicable | SI/UPPCL |  | 22/4/2026 | 24/4/2026
Finalise and Create the Group for CFW UAT | SI/UPPCL |  | 27/4/2026 | 30/4/2026
Create steering configurations to steer Cloud Firewall traffic for UAT Group | SI |  | 2026-01-05 | 2026-05-05 | bar: 2026-04-01 to 2026-05-05
Create CFW policies as per customer requirements | SI |  | 2026-01-05 | 2026-05-05
Fine-tune ports access as per operational requirements | SI/UPPCL |  | 2026-06-05 | 2026-08-05
UAT Acceptance of Cloud Firewall | UPPCL |  | 2026-06-05 | 2026-08-05
Production Rollout Phasewise | SI/UPPCL |  | 2026-11-05 | 15/5/26
Sign-off for Cloud Firewall | UPPCL |  | 18/5/26 | 20/5/26
5.DLP
Best practice/industry standard DLP policies configuration (web) | SI |  | 27/5/26 | 29/5/26
Configuration of DLP policies as per requirement shared by UPPCL (web) | SI |  | 2026-01-06 | 2026-05-06 | bar: 2026-04-01 to 2026-05-06
UAT | SI/UPPCL |  | 2026-08-06 | 2026-10-06
Testing & Fine Tuning of policies | SI/UPPCL |  | 2026-11-06 | 2026-12-06
UAT Sign-Off | UPPCL |  | 15/6/2026 | 17/6/2026
Production Rollout Phasewise | SI/UPPCL |  | 18/6/2026 | 26/6/2026
Sign-off for DLP Implementation | UPPCL |  | 29/6/2026 | 30/6/2026
6. NPA
Publisher and Broker Deployment | SI/UPPCL |  | 2026-01-07 | 2026-08-07 | bar: 2026-04-01 to 2026-08-04
Creation of private apps in Netskope tenant | SI/UPPCL |  | 2026-09-07 | 13/7/2026
Policy creation for NPA | SI/UPPCL |  | 14/7/2026 | 17/7/2026
Testing for NPA | SI/UPPCL |  | 20/7/2026 | 22/7/2026
Production Roll Out for all Users | SI/UPPCL |  | 23/7/2026 | 31/7/2026
Sign-off for NPA deployment | UPPCL |  | 2026-03-08 | 2026-06-08 | bar: 2026-04-01 to 2026-06-08
7. Project Handover
Knoledge Transfer Session | SI |  | 2026-07-08 | 2026-11-08 | bar: 2026-07-08 to 2026-08-04
EOC | SI |  | 2026-12-08 | 2026-12-08
Project Sign-Off | UPPCL |  | 13/8/2026 | 17/8/2026